## Notes
CSC480A Requirement
CSC480A students expect to complete the first tab -Product Backlog completely, as a minimum in to the Project proposal.
Students will also present the table in their project presentation in session 8.
Team needs to assign the clear responsibility to update this from their daily scrum meetings.
This spreadsheet will be a deliverable along with the Project Proposal
Disclaimer.
There are multiple methods to track Agile implementation/Development methodology.
What is provided here is more generic and one example and not by any means complete or final.
Students are encouraged to do more research on Agile websites to find even more suitable or better tracking tools.
Students are encouraged to innovate on their own as well for tracking their progress.
The whole objective in Agile is to keep it simple, easily understandable methods to track each iteration cycle.
Teams can add more tabs are each team sees the need.

## Team Roles
CSC480A - Team Roles Definition
Team # 2
| Team Member Name | Role 1 | Role 2 | Role 3 | Comments/Notes
1 | Matthew Parra | Scrum Master/Project Manager | Programmer | Tester | As team leader Matt is also the PM. He will also code the webservice
2 | Thomas Lowe | Product Owner | Programmer | Tester | Thomas came up with the idea and understands the user and their requirements
3 | Revanth Matha | Architect | OOD Designer | Scrum Master | Revanth has experience working with the entire technology stack
4 | Brian Hurst | GUI Designer | Programmer | Tester | Brian will help design and test the app end-to-end
5
Notes: This is part of the requirement to be shown in CSC480A presentation and screen shot in the proposal document
This needs to be maintained by one of the Leaders and reviewed before the start of each iteration, and make any changes.
Agile Roles: Product owner, Scrum Master, Project Manager, Architect (or Lead Designer), GUI designer, OOD Designers, Programmer(s), Tester(s), Quality checker, etc.
Check videos and other research materials as well to get a better ideas about roles.

## Product Bklog
Team # | 2
Project: | HOA application
Feature List and Its Associated Planning Data
| Feature Name/Scenario/Tasks | Priority | Implementation Iteration # | High Level Effort -Hrs | Comment 1 | Comments 2
1 | Login development | High | 1 | 20 | Developing the first GUI's for the user (login screen)
2 | Create Account development | High | 1 | 30 | Second GUI to develop is the creation of an account
3 | Repair Request development | High | 1 | 30 | This group of development are the apps main features.
4 | View Homeowners policies development | High | 2 | 60
5 | View Request Status development | High | 2 | 60
6 | View Pending Requests development | High | 2 | 60
7 | Policy and Rules update development | Med | 3 | 30
8 | Admin tools development | Med | 3 | 80 | Admin rights and privleges to add and remove users.
9 | Product Testing | High | 3 | 30 | Test/Repair Application for errors
10 | Quality Assurance | High | 4 | 30 | Complete Testing/Repair of applicaiton errors
11 | Change management | Low | 4 | 20 | For app updates or the addition of new last minute features.
|  |  | Total Project Hrs Est. | 450
Notes:
1. Platform and/or other infrastructure/technology enablers (e.g. data base setup) are needed, they need to identified (as features or Tasks) first for implementation and high on priority.
2. This tab needs to be completed as a part of CSC480A and submitted in addition to the Project Proposal

## User Story
Feature/Use case/Scenario | User Story ID | AS A <type of User> | I want to <perform some task> | So that I can <achieve this goal> | Test ID #
Send Requests | 1 | End User / Product Owner | Fill out a digital form | save time | 1
Store info in DB | 2 | Programmer | save data | data persistance | 2
View Requests | 3 | End User / Product Owner | see whats been saved | not deal with paper | 3
Approve/Deny Requests | 4 | Product Owner/User | pass judgement | turn service request into work or not | 4
Chat | 5 | Product Owner/User | communicate with tenent | ask user questions | 5
View Documents | 6 | Product Owner/User | see bylaws easily | reference hoa docs | 6
Sort Requests | 7 | Product Owner/User | find requests quicker | save time | 7
Search Requests | 8 | Product Owner/User | find requests quicker | save time | 8
Collect Money | 9 | Product Owner/User | pay for expenses | hire contractors | 9
Assign Task to Person | 10 | Product Owner/User | delegate request followup | speed up process step | 10
Create UI/UX | 11 | GUI Designer | mockup design | speed up development | 11
Create Webservices | 12 | Programmer | connect mobile to database | pass data | 12
Test edge cases | 13 | Tester | handle expections/errors | provide less support | 13
Create Cloud IAAS | 14 | Architect | procure hardware | create webservices & database | 14
Mobile App Env | 15 | Tester | configure dev, test, prod | test safely | 15
App Store Release | 16 | Product Owner/User | download app from store | use the app | 16
Database Scheme | 17 | Architect | plan data fields | integrate systems/pass data | 17
Mobile UI | 18 | Programmer | create UI Components | show user GUI | 18
Notes:
1. Each Feature can be decomposed further in User Stories to help clarify exact implementation and should help testers to prepare test plans and to execute them.
2. Start with high priority features and each feature may have more than one User Story (different IDs). This is an outcome of Use Cases broken down to User Scenarios to User story.

## Feature-Burn Down Charts
Burn Down Chart for Each Iteration
|  | Iteration 1 |  |  |  |  | Iteration 2 |  |  |  |  | Iteration 3 |  |  |  |  | Iteration 4
|  | Date | Feature/User Story/Task | Total Est Hrs. to Complete | Total Hrs. Completed | Total Hrs. Left | Date | Feature/User Story/Task | Total Est Hrs. to Complete | Total Hrs. Completed | Total Hrs. Left | Date | Feature/User Story/Task | Total Est Hrs to Complete | Total Hrs Completed | Total Hrs Left | Date | Feature/User Story/Task | Total Est Hrs to Complete | Total Hrs Completed | Total Hrs Left
Start Date | Day 1 | 2020-01-06 | AWS | 8 |  |  | 2020-01-20 | webservice | 6 |  |  | 2020-02-03 | chat | 3 |  |  | 2020-02-17 | attachments | 8
| Day 2 | 2020-01-07 | AWS | 8 |  |  | 2020-01-21 | webservice | 6 |  |  | 2020-02-04 | chat | 3 |  |  | 2020-02-18 | attachments | 8
| Day 3 | 2020-01-08 | Database | 4 |  |  | 2020-01-22 | webservice | 6 |  |  | 2020-02-05 | chat | 3 |  |  | 2020-02-19 | attachments | 8
| Day 4 | 2020-01-09 | Database | 4 |  |  | 2020-01-23 | webservice | 6 |  |  | 2020-02-06 | chat | 3 |  |  | 2020-02-20 | view documents | 8
| Day 5 | 2020-01-10 | DataBase | 4 |  |  | 2020-01-24 | webservice | 6 |  |  | 2020-02-07 | chat | 3 |  |  | 2020-02-21 | view documents | 8
| Day 6 | 2020-01-11 | Mobile UI-login | 8 |  |  | 2020-01-25 | webservice | 6 |  |  | 2020-02-08 | chat | 3 |  |  | 2020-02-22 | view documents | 8
| Day 7 | 2020-01-12 | Mobile UI-register | 8 |  |  | 2020-01-26 | webservice | 6 |  |  | 2020-02-09 | chat | 3 |  |  | 2020-02-23 | view documents | 8
| Day 8 | 2020-01-13 | Mobile UI-service request | 8 |  |  | 2020-01-27 | admin-view service request | 8 |  |  | 2020-02-10 | chat | 3 |  |  | 2020-02-24 | testing | 8
| Day 9 | 2020-01-14 | Mobile UI-service request | 8 |  |  | 2020-01-28 | admin-view service request | 8 |  |  | 2020-02-11 | search/sort | 4 |  |  | 2020-02-25 | testing | 8
| Day 10 | 2020-01-15 | Mobile UI-service request | 8 |  |  | 2020-01-29 | admin-view service request | 8 |  |  | 2020-02-12 | search/sort | 4 |  |  | 2020-02-26 | testing | 8
| Day 11 | 2020-01-16 | Mobile UI-service request | 8 |  |  | 2020-01-30 | admin-view service request | 8 |  |  | 2020-02-13 | search/sort | 4 |  |  | 2020-02-27 | app store | 2
| Day 12 | 2020-01-17 | Mobile UI-service request | 8 |  |  | 2020-01-31 | admin-approve deny | 4 |  |  | 2020-02-14 | search/sort | 4 |  |  | 2020-02-28 | app store | 2
| Day 13 | 2020-01-18 | Mobile UI-service request | 8 |  |  | 2020-02-01 | admin-assign workorder | 4 |  |  | 2020-02-15 | search/sort | 4 |  |  | 2020-02-29 | app store | 2
End Date | Day 14 | 2020-01-19 | Mobile UI-service request | 8 |  |  | 2020-02-02 | admin-view service request | 8 |  |  | 2020-02-16 | search/sort | 4
Draw a Chart to show the progress each day
By the scrum Mater.

## Test Plan Chart
|  | Project Name |  |  | Browser:
|  | Test Case ID |  |  | Version:
|  | Written By: |  |  | Description:
|  | Tested By: |  |  | Tested On:
Iteration # | Feature/Story ID/Task Name | Test # | Date | Action | Expected Results | Actual Results | Pass?

## Risk Matrix
Project Risk Management Matrix
Note - Copy the information/data from the Project Proposal Section 8 - Project Issues and Risk
Follow through with this during implementation and one of the leaders should be in charge.
Team can add more and close under status when done mitigating the risk.
Issue - the obstacle exists now
Risk - Anticipated obstacle in the future.
| Issue or Risk Brief Detail | Risk Probability: High, Medium, Low | Mitigation Plan | Responsibility | Status: Open, WIP, closed
1 | Due Date: The given time to properly develop the application features is too short. | High | Create a through time table for each feature and its creation | Matthew Parra | WIP
2 | Performance: The application does not perform as intended, ie. slow or doesn’t produce correct results | Medium | Run as many unit tests within means to prevent any unforeseen issues | Revanth Matha | WIP
3 | Feature Abstraction: There are too many features requested to include in the application | Low | Review and identify the key requirements that are necessary to create an application that fills the needs of the Homeowners Association and the Homeowners | Brian Hurst | WIP
4 | Adoption: The application is too difficult to deploy, ie. database deployment | Medium | Provide key documents necessary to deploy the application within the Homeowners Association’s abilities | Thomas Lowe | Open
5 | Hardware limitations: Not all Homeowners and board members have smart phones/data plans to accommodate application use | Medium | If the homeowner or board member is unable to facilitate the application, templates with similar forms will be provided | Revanth Matha | WIP
6 | Understanding: Board members and Homeowners do not understand how to use the application | Low | Provide documentation that carefully illustrates the use of the application, from initial download to the various features within the application | Thomas Lowe | WIP
7 | Management Changes: New members to the board of supervisors who require new features | High | Provide new board member or members with documentation that highlights current features and how they may facilitate their requests already | Matthew Parra | Open
8
9
10
11
12
13
14
15
16
17